## TASK
task_code | status_code | wbs_id | task_name | complete_pct | act_start_date | act_end_date | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | Activity % Complete(%) | Actual Start | Actual Finish | Delete This Row
SS.SC2.PC.RD5-A.870 | Completed | CP06-UP-49.CON.SC2.A5.5-A.PCS | Excavation for RTU Panels Foundation | 100 | 2026-06-03 08:00 | 2026-06-05 16:00
SS.SC2.PC.RD5-A.930 | Completed | CP06-UP-49.CON.SC2.A5.5-A.PCS | Installation of RTU Panels Foundation | 100 | 2026-06-07 08:00 | 2026-06-09 16:00
SS.SC2.PC.RD5-A.960 | Completed | CP06-UP-49.CON.SC2.A5.5-A.PCS | Backfilling for RTU Panels | 100 | 2026-06-11 08:00 | 2026-06-13 16:00
SS.SC2.PC.RD5-B.1070 | Completed | CP06-UP-49.CON.SC2.A5.5-B.PCS | Excavation for RTU Panels Foundation | 100 | 2026-06-03 08:00 | 2026-06-05 16:00
SS.SC2.PC.RD5-B.1130 | Completed | CP06-UP-49.CON.SC2.A5.5-B.PCS | Installation of RTU Panels Foundation | 100 | 2026-06-07 08:00 | 2026-06-09 16:00
SS.SC2.PC.RD5-B.1160 | Completed | CP06-UP-49.CON.SC2.A5.5-B.PCS | Backfilling for RTU Panels | 100 | 2026-06-11 08:00 | 2026-06-13 16:00
SS.SC2.PC.RD5-C.1070 | Completed | CP06-UP-49.CON.SC2.A5.5-C.PCS | Excavation for RTU Panels Foundation | 100 | 2026-06-03 08:00 | 2026-06-05 16:00
SS.SC2.PC.RD5-C.1130 | Completed | CP06-UP-49.CON.SC2.A5.5-C.PCS | Installation of RTU Panels Foundation | 100 | 2026-06-07 08:00 | 2026-06-09 16:00
SS.SC2.PC.RD5-C.1160 | Completed | CP06-UP-49.CON.SC2.A5.5-C.PCS | Backfilling for RTU Panels | 100 | 2026-06-11 08:00 | 2026-06-13 16:00
SS.SC2.PC.RD5-D.870 | Completed | CP06-UP-49.CON.SC2.A5.5-D.PCS | Excavation for RTU Panels Foundation | 100 | 2026-06-03 08:00 | 2026-06-05 16:00
SS.SC2.PC.RD5-D.930 | Completed | CP06-UP-49.CON.SC2.A5.5-D.PCS | Installation of RTU Panels Foundation | 100 | 2026-06-07 08:00 | 2026-06-09 16:00
SS.SC2.PC.RD5-D.960 | Completed | CP06-UP-49.CON.SC2.A5.5-D.PCS | Backfilling for RTU Panels | 100 | 2026-06-11 08:00 | 2026-06-13 16:00
SS.SC2.PC.RD5-1.1090 | Completed | CP06-UP-49.CON.SC2.A5.MR5.1.PCS | Excavation for RTU Panels Foundation | 100 | 2026-05-04 | 2026-05-08
SS.SC2.PC.RD5-1.1160 | Completed | CP06-UP-49.CON.SC2.A5.MR5.1.PCS | Installation of RTU Panels Foundation | 100 | 2026-05-04 | 2026-05-08
SS.SC2.PC.RD5-1.1190 | Completed | CP06-UP-49.CON.SC2.A5.MR5.1.PCS | Backfilling for RTU Panels | 100 | 2026-05-04 | 2026-05-08
SS.SC2.RW.RD4-A.1010 | Completed | CP06-UP-49.CON.SC2.A6.4-A.RW | Installation of Fire Haydrant Pillars | 100 | 2025-09-30 | 2026-05-08
SS.SC2.DR.RD4-A.240 | In Progress | CP06-UP-49.CON.SC2.A6.4-A.DR.MH | Manhole Cover | 50 | 2026-05-04
SS.SC2.RW.RD4-B.1010 | Completed | CP06-UP-49.CON.SC2.A6.4-B.RW | Installation of Fire Haydrant Pillars | 100 | 2025-09-30 | 2026-05-08
SS.SC2.RW.RD4-B.980 | In Progress | CP06-UP-49.CON.SC2.A6.4-B.RW | Installation of Curbstone | 95 | 2026-04-20
SS.SC2.RW.RD4-B.1000 | In Progress | CP06-UP-49.CON.SC2.A6.4-B.RW | Installation of Paving Blocks | 95 | 2026-04-24
SS.SC2.DR.RD4-B.210 | In Progress | CP06-UP-49.CON.SC2.A6.4-B.DR.MH | Accessories and Stairs | 50 | 2026-05-04
SS.SC2.RW.RD4-C.1010 | Completed | CP06-UP-49.CON.SC2.A6.4-C.RW | Installation of Fire Haydrant Pillars | 100 | 2025-09-30 | 2026-05-08
SS.SC2.DR.RD4-C.230 | In Progress | CP06-UP-49.CON.SC2.A6.4-C.DR.MH | Accessories and Stairs | 50 | 2026-05-04
SS.SC2.RW.RD4-D.1180 | Completed | CP06-UP-49.CON.SC2.A6.4-D.RW | Installation of Fire Haydrant Pillars | 100 | 2025-09-30 | 2026-05-08
SS.SC2.RW.RD4-D.1150 | In Progress | CP06-UP-49.CON.SC2.A6.4-D.RW | Installation of Curbstone | 95 | 2026-04-24
SS.SC2.RW.RD4-D.1170 | In Progress | CP06-UP-49.CON.SC2.A6.4-D.RW | Installation of Paving Blocks | 95 | 2026-04-24
SS.SC2.DR.RD4-D.250 | In Progress | CP06-UP-49.CON.SC2.A6.4-D.DR.MH | Accessories and Stairs | 50 | 2026-05-04
SS.SC2.IR.RD4-D.610 | Completed | CP06-UP-49.CON.SC2.A6.4-D.IR.VC | Chamber Cover | 100 | 2026-05-04 | 2026-05-08
SS.SC2.RW.RD4-1.1260 | Completed | CP06-UP-49.CON.SC2.A6.MR4.1.RW | Installation of Fire Haydrant Pillars | 100 | 2025-09-30 | 2026-05-08
SS.SC2.DR.RD4-1.210 | In Progress | CP06-UP-49.CON.SC2.A6.MR4.1.DR.MH | Accessories and Stairs | 50 | 2026-05-04
SS.SC2.RW.RD4-2.1260 | Completed | CP06-UP-49.CON.SC2.A6.MR4.2.RW | Installation of Fire Haydrant Pillars | 100 | 2025-09-30 | 2026-05-08
SS.SC2.DR.RD4-2.210 | In Progress | CP06-UP-49.CON.SC2.A6.MR4.2.DR.MH | Accessories and Stairs | 50 | 2026-05-04
SS.SC3RW.RD3-A.1010 | Completed | CP06-UP-49.CON.SC3.A7.3-A.RW | Installation of Fire Haydrant Pillars | 100 | 2025-09-30 | 2026-05-08
SS.SC3.EL.RD3-A.710 | In Progress | CP06-UP-49.CON.SC3.A7.3-A.EL.PDO | Installation of Coffret | 25 | 2026-05-04
SS.SC3.EL.RD3-B.710 | In Progress | CP06-UP-49.CON.SC3.A7.3-B.EL.PDO | Installation of Coffret | 20 | 2026-05-04
SS.SC3.EL.RD3-C.710 | In Progress | CP06-UP-49.CON.SC3.A7.3-C.EL.PDO | Installation of Coffret | 20 | 2026-05-04
SS.SC3RW.RD3-D.1010 | In Progress | CP06-UP-49.CON.SC3.A7.3-D.RW | Installation of Fire Haydrant Pillars | 80 | 2026-05-04
SS.SC3RW.RD3-1.1310 | In Progress | CP06-UP-49.CON.SC3.A7.MR3.1.RW | Installation of Fire Haydrant Pillars | 80 | 2026-05-04
SS.SC3.EL.RD3-1.750 | Completed | CP06-UP-49.CON.SC3.A7.MR3.1.EL.SP | Excavation for Spare Conduts | 100 | 2026-05-04 | 2026-05-08
SS.SC3.EL.RD3-1.830 | Completed | CP06-UP-49.CON.SC3.A7.MR3.1.EL.SP | Laying of Spare Conduts | 100 | 2026-05-04 | 2026-05-08
SS.SC3.EL.RD3-1.950 | Completed | CP06-UP-49.CON.SC3.A7.MR3.1.EL.SP | Backfilling for Spare Conduts | 100 | 2026-05-04 | 2026-05-08
SS.SC3RW.RD3-2.1260 | In Progress | CP06-UP-49.CON.SC3.A7.MR3.2.RW | Installation of Fire Haydrant Pillars | 80 | 2026-05-04
SS.SC3.EL.RD3-2.930 | In Progress | CP06-UP-49.CON.SC3.A7.MR3.2.EL.SL | Excavation for Street Lighting Poles Foundation | 50 | 2026-05-04
SS.SC3.EL.RD3-2.1010 | In Progress | CP06-UP-49.CON.SC3.A7.MR3.2.EL.SL | Installation of Street Lighting Poles Foundation | 50 | 2026-05-04
SS.SC3.EL.RD3-2.1100 | In Progress | CP06-UP-49.CON.SC3.A7.MR3.2.EL.SL | Backfilling for Street Lighting Poles | 50 | 2026-05-04
SS.SC3.EL.RD3-2.750 | Completed | CP06-UP-49.CON.SC3.A7.MR3.2.EL.SP | Excavation for Spare Conduts | 100 | 2026-05-04 | 2026-05-08
SS.SC3.EL.RD3-2.830 | Completed | CP06-UP-49.CON.SC3.A7.MR3.2.EL.SP | Laying of Spare Conduts | 100 | 2026-05-04 | 2026-05-08
SS.SC3.EL.RD3-2.940 | Completed | CP06-UP-49.CON.SC3.A7.MR3.2.EL.SP | Backfilling for Spare Conduts | 100 | 2026-05-04 | 2026-05-08
SS.SC3.RW.CL1-A.150 | In Progress | CP06-UP-49.CON.SC3.A8.CL1-A.RW | Installation of Fire Haydrant Pillars | 50 | 2026-05-04
SS.SC3.RW.CL1-A.120 | In Progress | CP06-UP-49.CON.SC3.A8.CL1-A.RW | Aggregate Subbase Course | 25 | 2026-05-04
SS.SC3.RW.CL1-B.150 | In Progress | CP06-UP-49.CON.SC3.A8.CL1-B.RW | Installation of Fire Haydrant Pillars | 50 | 2026-05-04
SS.SC3.RW.CL1-B.120 | In Progress | CP06-UP-49.CON.SC3.A8.CL1-B.RW | Aggregate Subbase Course | 25 | 2026-05-04
SS.SC3.RW.CL1-C.150 | In Progress | CP06-UP-49.CON.SC3.A8.CL1-C.RW | Installation of Fire Haydrant Pillars | 50 | 2026-05-04
SS.SC3.RW.CL1-D.150 | In Progress | CP06-UP-49.CON.SC3.A8.CL1-D.RW | Installation of Fire Haydrant Pillars | 50 | 2026-05-04
SS.SC3RW.CL1-1.1260 | In Progress | CP06-UP-49.CON.SC3.A8.MR-CL1.1.RW | Installation of Fire Haydrant Pillars | 50 | 2026-05-04
SS.SC3.RW.CL1-1.120 | In Progress | CP06-UP-49.CON.SC3.A8.MR-CL1.1.RW | Aggregate Subbase Course | 40 | 2026-04-24
SS.SC3RW.CL1-2.1260 | In Progress | CP06-UP-49.CON.SC3.A8.MR-CL1.2.RW | Installation of Fire Haydrant Pillars | 50 | 2026-05-04
SS.SC3.RW.CL1-2.120 | In Progress | CP06-UP-49.CON.SC3.A8.MR-CL1.2.RW | Aggregate Subbase Course | 40 | 2026-04-24
SS.UB.IRRT.1380 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.PLUM | above ground waste piping | 50 | 2026-05-04
SS.UB.IRRT.1450 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.PLUM | submersible sump pumps | 25 | 2026-05-04
SS.UB.IRRT.1290 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.PLUM | inspection chamber | 50 | 2026-05-04
SS.UB.IRRT.1300 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.PLUM | slow down chamber | 50 | 2026-05-04
SS.UB.IRRT.1240 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.LC.ENV | feeding connections HDPE pipes | 60 | 2026-05-04
SS.UB.IRRT.1270 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.LC.ENV | ductile iron pipes for overflow | 60 | 2026-05-04
SS.UB.IRRT.1360 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.LC.ENV | water meters | 60 | 2026-05-04
SS.UB.IRRT.1410 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.LC.ENV | isolation gate valves | 60 | 2026-05-04
SS.UB.IRRT.1350 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.PLUM | below ground waste piping | 50 | 2026-05-04
SS.UB.IRRT.1540 | In Progress | CP06-UP-49.CON.UB.IRT.MEP.PLUM | facility water distribution piping | 25 | 2026-05-04
SS.UB.EMCC.1030 | Completed | CP06-UP-49.CON.UB.EMCC.FOUN | plain concrete footings concrete pouring | 100 | 2026-05-04 | 2026-05-08
SS.UB.EMCC.1040 | Completed | CP06-UP-49.CON.UB.EMCC.FOUN | reinforced concrete footings form work | 100 | 2026-05-04 | 2026-05-08
SS.UB.EMCC.1050 | In Progress | CP06-UP-49.CON.UB.EMCC.FOUN | reinforced concrete footings steel fixing | 90 | 2026-05-04
SS.SC3.EL.CL1-1.1250 | Completed | CP06-UP-49.CON.SC3.A8.MR-CL1.1.EL.SUB | Backfilling for Substation | 100 | 2026-05-04 | 2026-05-08
SS.MR.TL.CL1-6.930 | Completed | CP06-UP-49.CON.CL1-6.TLE.SP.CH | Backfilling for Manholes | 100 | 2026-04-20 | 2026-05-08
SS.MR.TL.CL1-6.1010 | Completed | CP06-UP-49.CON.CL1-6.TLE.SP.CD | Backfilling | 100 | 2026-04-20 | 2026-05-08
SS.MR.TL.CL1-6.1020 | Completed | CP06-UP-49.CON.CL1-6.TLE.ORA.CD | Backfilling | 100 | 2026-04-20 | 2026-05-08
SS.MR.TL.CL1-6.1040 | Completed | CP06-UP-49.CON.CL1-6.TLE.ORA.CH | Backfilling for Manholes | 100 | 2026-04-20 | 2026-05-08
SS.MR.IR.RD2-B.170 | In Progress | CP06-UP-49.CON.1.2-B.IR.ML | Excavation | 30 | 2026-05-04
SS.MR.IR.RD2-B.190 | In Progress | CP06-UP-49.CON.1.2-B.IR.ML | Pipe Bedding | 30 | 2026-05-04
SS.MR.IR.RD2-B.210 | In Progress | CP06-UP-49.CON.1.2-B.IR.ML | Pipe Laying | 30 | 2026-05-04
SS.MR.IR.RD2-B.270 | In Progress | CP06-UP-49.CON.1.2-B.IR.ML | Backfilling | 30 | 2026-05-04
SS.MR.PW.RD2-B.180 | In Progress | CP06-UP-49.CON.1.2-B.PW.ML | Excavation | 30 | 2026-05-04
SS.MR.PW.RD2-B.200 | In Progress | CP06-UP-49.CON.1.2-B.PW.ML | Pipe Bedding | 30 | 2026-05-04
SS.MR.PW.RD2-B.220 | In Progress | CP06-UP-49.CON.1.2-B.PW.ML | Pipe Laying | 30 | 2026-05-04
SS.MR.PW.RD2-B.280 | In Progress | CP06-UP-49.CON.1.2-B.PW.ML | Backfilling | 30 | 2026-05-04

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=m/d/yyyy CurrencyFormat=US Dollar